## Logs
No | Short Description | Notes | Type | Priority | Size | Cleared | Status
1 | Stream Input Node | Stream input node for loading inputs to the network | Deficiency | 4. Essential | 2. Medium | Yes
2 | Stream Target Node | Stream target node for loading targets into the network | Deficiency | 4. Essential | 2. Medium | Yes
3 | Network Serialization | Network Serialisation for loading & persisting the network (use policy objects) | Deficiency | 4. Essential | 3. Large | Yes
4 | Build plug hierarchy | Pluggable inheritance a la Alexandrescu | Refactor | 3. High | 3. Large | No
5 | Simplify connections | Connections are *still* too complex - simplify | Refactor | 3. High | 3. Large | No
6 | Do TODOs | Clean up all outstanding TODOs | Enhancement | 2. Middle | 3. Large | No
7 | Result Node | Result Node - Required for unit testing | Enhancement | 4. Essential | 1. Small | Yes
8 | Rename proj to NeuT | Needed for new name | Enhancement | 3. High | 2. Medium | No
9 | Build Win32 | For execution on the server | Enhancement | 2. Middle | 3. Large | No
10 | Remote invokation | For execution on the server | Enhancement | 2. Middle | 3. Large | No
11 | T0 Initialisation | Use default constructir to init T types with zero | Enhancement | 2. Middle | 1. Small | Yes
12 | Build Qt Gui | Build a gui to wrap the library using Qt | Enhancement | 2. Middle | 4. Huge | No
13 | Fix previous weight | Make 'previous weight' the same as 'current weight' | Bug | 4. Essential | 1. Small | Yes | Not Implemented - causes worse learning performance
14 | Remove IActivatable | Get rid of the over-engineered superfluous Iactivatable | Refactor | 3. High | 2. Medium | No
15 | Doxygen | Use doxygen to generate documentation | Enhancement | 3. High | 2. Medium | No
16 | ResizeUtil | Add Utils namespace & add template funtion to resize array-like functions | Refactor | 2. Middle | 2. Medium | Yes
17 | OnAddConnection | Change onAddConnection to show the slot number | Deficiency | 3. High | 2. Medium | No
18 | Boost::bind | Use boost::bind for the for_each pieces of code | Refactor | 2. Middle | 2. Medium | No
19 | Generic resizing | Of connectors, weight, inputs etc (include index) | Deficiency | 4. Essential | 2. Medium | Yes
20 | Exceptions | Determine & implement excpetion handling strategy | Deficiency | 4. Essential | 3. Large | No
21 | Typedefs | Tidy up all typedefs using "typename" | Refactor | 2. Middle | 2. Medium | No
22 | lexical_cast | Check that lexical_cast is actually required for accurate serialization | Refactor | 4. Essential | 1. Small | No
23 | Periodic saving node | Add container node which serializes it's child every N iteration | Enhancement | 4. Essential | 2. Medium | No
24 | FrontAndBack Activating Node | Add container node which translates front/back activation to both front and back | Enhancement | 4. Essential | 2. Medium | No
25 | N Activating node | Add container node which turns a single activation into N activations of it's children | Enhancement | 4. Essential | 2. Medium | No
26 | Floating point accuracy | Change debug printing to give higher precision | Enhancement | 4. Essential | 1. Small | No
27 | Template types | Go through replacing "double" with "T" where needed | Refactor | 3. High | 1. Small | No
28
29
30
31

## Enums
Type | Priority | Size | Complete
Bug | 4. Essential | 4. Huge | Yes
Deficiency | 3. High | 3. Large | No
Enhancement | 2. Middle | 2. Medium
Refactor | 1. Low | 1. Small